## Risk-based assumptions
ASSUMPTIONS
Assumption name | Value | Risks identified by DT, DD, RM | Initial range | Source | Proposed mitigations | Updated range | Comments | Correlations
Name of the assumption used in the decision model. For example, USD/EUR exchange rate, sales growth from year to year or inflation | Value of the assumption originally used by management | List of risks identified that may impact each assumption, both positively and negatively. Sources of information could be historical data, external industry research, interviews with experts or other. More than one risk can be identified for each assumption. Need to also apply Key assumptions check methodology. | Based on the risks identified the management has to determine the 90% confidence interval for the assumption. The range of values in which actual may fall 90% of the time. The management should also determine the likely shape of the distribution used for representing this assumption behavior (PERT, lognormal, poisson, etc.) | Source of information and justification | Once the first simulation is performed one of the following is possible: 1. The likelihood of achieving objective is acceptable, no further mitigation is required 2. The likelihood of achieving objective is not acceptable, the management needs to come up with additional mitigations and record them here 3. The decision is too risky and needs to be droped | Based on the risks identified and the additional mitigations the management has to update the 90% confidence interval for the assumption and re-run the simulation | Source of information, justification and other comments | Correlations between assumptions (-1 to 1)
Risk description | Probability | Impact |  |  | Variable A | Variable B
The description of the risk scenario, for example consutruction delay | Probability that risk happens, can be represented by Bernoulli distribution | Overview of the different scenarios how this risk may affect the financial model if it does occur, for example delay be zero, 1, 3 or 15 months
This is a sample template to illustrate how risk analysis can be integrated into planning and decision making. This page should be adopted and replace the inputs or assumptions used ina financial model.
Add volatility to existing assumptions
2
Run first simulation
3
Run second simulation
Add risk events (optional)
1A
1B
Sometimes it may be necessary to add events that if happen will have a dramatic effect on the business. Usually such impact is not captured in the volatility above. Examples could include political events that if happen may affect many parts of the financial model or a major delay in opening a new plant.
Add correlations
1С
To keep the model outputs realistic it is critical to identify and document correlations between assumptions. Use the space below to create correlation tables and paste the correlations into the register above.